## Slide 1: KESTREL P2 Design Review
27 August 2026 · Product, Engineering, Sourcing, Marketing, Finance

## Slide 2: Agenda
P2 results against targets
Armrest bracket failure (T5)
Options and costs
Assembly time
Customer voice
Decision needed

## Slide 3: P2 against targets
Metric | Target | P2 result | Status
Base diameter | ≤ 600 mm | 592 mm | OK
Seat width | 460–490 mm | 475 mm | OK
Mass | — | 13.2 kg | —
Carton volume | ≤ 0.12 m³ | 0.118 m³ | OK
Shell fatigue (T2) | 120,000 cycles | 120,000, no failure | OK
Armrest fatigue (T5) | 60,000 cycles | 38,500 / 41,200 | FAIL
Assembly time (T9) | ≤ 10 min | 11.6 min mean | FAIL
Recycled content (BOM estimate) | ≥ 50% | 47% | MISS
Unit cost at 5k (baseline) | ≤ USD 120 | USD 116.85 | OK
Notes: Recycled content and unit cost come from the Sourcing quote workbook, July 2026.

## Slide 4: Armrest bracket failure (T5)
Zinc die-cast bracket KS-204 cracked at 38,500 and 41,200 cycles (target 60,000)
Crack starts at the R0.5 mm inner radius next to the mounting boss
Sectioning found gas porosity up to 0.4 mm in the crack origin
  FEA peak stress 212 MPa at the radius under the TP-12 load
Notes: Hypotheses from TR-2026-031: H1 sharp radius, H2 casting porosity, H3 bolt preload loss.

## Slide 5: Options for the armrest fix
Option | Description | Unit cost delta | Tooling | Timeline
A | Zinc, R2.0 radius + rib | +USD 0.36 | USD 4,800 | +3 weeks
B | Stamped steel bracket | +USD 1.10 | USD 11,500 | +5 weeks
C | Flip-up armrest assembly | +USD 4.90 | USD 26,000 | +8 weeks
Notes: Unit cost deltas are per chair at 5,000 units and include both armrests.

## Slide 6: Assembly time by tester (minutes)
Chart: 
| Tester 1 | Tester 2 | Tester 3 | Tester 4 | Tester 5
Assembly time (min) | 9.1 | 10.8 | 11.4 | 12.5 | 14.2
Notes: Target is 10 minutes. Testers 1 and 2 used the printed guide; the backrest-to-mechanism step took longest for everyone. Captive screws on the backrest are estimated to save about 2 minutes.

## Slide 7: Customer voice
“I want armrests that fold away when I am typing, then come back when I read.” (P08)
“It is a great chair, it is just enormous. The armrests hit the desk so I cannot pull in.” (P05)
“Tell me the percentage of recycled plastic and I will believe you.” (P09)

## Slide 8: Decision needed
Select armrest option A, B or C for P3
Close the recycled-content gap (EcoLine mechanism?)
Approve captive-screw backrest to cut assembly time
Keep landed unit cost ≤ USD 120 at 5,000 units
Notes: Finance will not approve a configuration above USD 120 landed cost without a price change.